## Gantt Chart
Week |  | - | Welcome | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Week Start Date |  | 2021-08-09 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18
Week Info |  | 2021-08-09: Holiday; 2021-09-20: Freshers; 2021-11-01: Reading; 2021-12-13: Holiday; 2021-12-20: Holiday; 2021-12-27: Holiday; 2022-01-03: Holiday; 2022-02-14: Reading; 2022-03-28: Holiday; 2022-04-04: Holiday; 2022-04-11: Holiday
1) PID | bar: 2021-08-09 to 2021-11-01
1.1) Concept Initiation | bar: 2021-08-09
1.2) Background Research | bar: 2021-08-09
1.3) Complete the PID Form | bar: 2021-08-09 to 2021-09-20
1.4) Refine the PID Form | bar: 2021-09-20 to 2021-11-01
2) Analysis/Design | bar: 2021-09-20 to 2021-11-01
2.1) Background Research | bar: 2021-09-20 to 2021-10-11
2.2) Feasibility Study | bar: 2021-09-27 to 2021-10-11
2.3) Game Architecture | bar: 2021-10-04 to 2021-10-18
2.4) Database Design | bar: 2021-10-18 to 2021-11-01
3) Prototype Development | bar: 2021-11-01 to 2022-01-31
3.1) Single player can connect | bar: 2021-11-01 to 2021-11-15
3.2) Multiple players can connect | bar: 2021-11-15 to 2021-11-29
3.3) Can interact with base features | bar: 2021-11-29 to 2021-12-27
3.4) Can interact with other features | bar: 2021-12-27 to 2022-01-24
3.5) Add finishing details | bar: 2022-01-24 to 2022-01-31
4) Testing/Evaluation/Validation | bar: 2022-01-31 to 2022-02-07
4.1) Produce a Test Plan | bar: 2022-01-31 to 2022-02-07
4.2) Perform Testing | bar: 2022-01-31 to 2022-02-07
4.3) Evaluate and validate results | bar: 2022-02-07
5) Assessments
5.1) Final Report
5.2) E-Logbook
5.3) Demo to supervisor | bar: 2022-02-07 to 2022-02-14
5.4) Poster/presentation | bar: 2022-02-14 to 2022-02-28
5.5) Project Presentation & Demo | bar: 2022-04-04 to 2022-04-18
Deadlines |  | 2021-10-04: 8/10/2021 - PID Submission; 2021-11-01: 05/11/2021 - Revised PID Submission; 2022-01-17: 21/01/2022 - Feedback Form Submission; 2022-02-21: 25/02/2022 - Poster/Presentation Submission; 2022-04-04: 22/04/2022 - E-Logbook Submission
[24 empty] | Reading Week - Demo to supervisor for feedback | [6 empty] | 22/04/2022 - Final Report Submission
[26 empty] | Week 8 (TBD) - Poster/Presentation will be displayed |  |  |  |  | Summer TBD - Presentation & Demo
Sessions |  | 2021-09-27: Week 1 - Training Sessions 1, 2 & 3; 2021-10-25: Week 5 - Training Sessions 4 & 5; 2021-11-22: Week 9 (TBD) - Interactive Session 1; 2022-02-28: Week 8 (TBD) - Interactive Session 2
[8 empty] | Week 5 - Project Assessment Instruction |  |  |  | Weak 9 (TBD) Polly Vacher AI Lab 185 (or Online Teams Meeting)